## CFG
ListCategory | ListSystem | ListPriority | ListStatus
Performance | Build | Low | Not Started
New Functionality | Rendering | Medium | In Progress
Refactoring | Audio | High | On Hold
Bug-fixing | Configuration | Critical | Done
Other | Gameplay |  | Aborted
UI
Other

## DATA
№ | Category | System | Priority | Status | Name | Description
1 | Refactoring | Configuration | High | In Progress | Decide on and implement a configuration format | Decide what format to use for configs(CSV, INI, JSON, custom), what structure to use for storage on disk(everything in 1 file, each in its own file, binary format, etc.), what system to use in app(list of strings, tree, other)
2 | Refactoring | Configuration | High | In Progress | Refactor configurations of System and Application | Refactor the configs of all managers/components/containers and all UI configs.
3 | New Functionality | Build | Low | Not Started | Build for Emscripten | Self-explanatory
4 | New Functionality | Build | Low | Not Started | Build for Android | Self-explanatory
5 | Performance | Rendering | Medium | Not Started | Improve rendering performance | Improve performance, namely, why is SDL_RenderPresent using so much GPU?
6 | Refactoring | Audio | Low | Not Started | Refactor the audio system | Refactor and add new functionality to the audio system
7 | Refactoring | UI | Medium | Not Started | Refactor the UI system | Refactor(how to handle menus and components - polymorphically, more verbose) and add new functionality to the UI system(new components)
8 | New Functionality | Rendering | Medium | Not Started | Add new functionality to images and texts | Refactor and add new functionality(animations, text effects, etc.)
9 | New Functionality | Rendering | High | Not Started | Refactor texts and images storage and handling | Refactor the way texts and images are stored(use something similar to the DynamicText)
10 | Performance | Other | Medium | Not Started | Use custom allocators for std containers | Improve memory usage by adding allocators for std containers(arena, pool, etc.)
11 | New Functionality | Gameplay | Low | Not Started | Create a small game | Tower defense
12 | New Functionality | Rendering | Medium | Not Started | Add graphing/shapes drawing | Add the main primitives to render(point, line, spline, circle, rectangle, etc.) and functionality to easily create and render them to support in-app creation and handling of them
13 | New Functionality | Other | Low | Not Started | Add editor | Decide how to make it(separate project, in-app, should it use ImGui, etc.)
14 | New Functionality | Other | Low | Not Started | Add networking | This would require a lot of work
15 | Other | Other | Low | Not Started | Create a logo, think of better names of the engine and apps, etc. marketing
16 | Refactoring | Other | Medium | Not Started | Refactor input system | Review how input events are handled and improve them, add support for typing text, key modulation, etc.
17 | Refactoring | Other | Low | Not Started | Review logging | Can I improve the logging system? Maybe add more color and formatting options(format only some text in a line, instead of formatting the whole line)
18 | Refactoring | Other | Low | Not Started | Use SDL3 | Try to use SDL3 library
19 | New Functionality | Other | Low | Not Started | Entity component system | Use ECS for System and Application(extensive research in this area shows negligible potential benefits, if any)
20
21
22
23
24
25
26
27
28
29
30